## Sheet1
Action | Responsible | Start Date | End Date | Budget | Status | Progress | Note
week 1 Reseaching | [6 empty] | we must make up
ESP 32 Module |  | 30/01/2023 | 30/01/2023 | None | started | 100%
Fingerprint sensor |  | 30/01/2023 | 30/01/2023 | None | started | 100%
OLED Module |  | 30/01/2023 | 30/01/2023 | None | started | 100%
Dicussing | Group |  |  | None | started | 100%
week 2 Hardware | [6 empty] | we must make up
ESP 32 Module |  | 2023-06-02 | 2023-06-02 | None | Not start | 70% | buy ESP 32 module
Fingerprint + OLED DIsplay |  | 2023-06-02 | 2023-06-02 | None | Not start | 80% | buy OLED Display
Dicussing | Group |  |  | None | Not start
week 3 Reseaching | [6 empty] | we must make up
ESP 32 +Data base |  | 13/02/2023 | 13/02/2023 | None | Not start | 50% | Reseaching how to connect
ESP 32 + Fingerprint sensor |  | 13/02/2023 | 13/02/2023 | None | Not start | 50% | Reseaching how to connect
ESP 32 + OLED display |  | 13/02/2023 | 13/02/2023 | None | Not start | 50%
Dicussing | Group |  |  | None | Not start
week 4 software | [6 empty] | we must make up
Arduino IDE |  | 20/02/2023 | 20/02/2023 | None | Not start | 30%
MIT to build app |  | 20/02/2023 | 20/02/2023 | None | Not start | 20%
Mashable to build app |  | 20/02/2023 | 20/02/2023 | None | Not start | 20%
Dicussing | Group |  |  | None | Not start | 30%
week 5 software testing | [6 empty] | we must make up
Arduino IDE |  | 27/02/2023 | 27/02/2023 | None | Not start | 30%
MIT to build app |  | 27/02/2023 | 27/02/2023 | None | Not start | 20%
Mashable to build app |  | 27/02/2023 | 27/02/2023 | None | Not start | 20%
Dicussing | Group |  |  | None | Not start | 30%
week 6 software design | [6 empty] | we must make up
Cuircit design |  | 2023-06-03 | 2023-06-03 | None | Not start | 30%
database design |  | 2023-06-03 | 2023-06-03 | None | Not start | 30%
MIT to build app design |  | 2023-06-03 | 2023-06-03 | None | Not start | 20%
Dicussing | Group |  |  | None | Not start | 30%
week 7 connecting | [6 empty] | we must make up
Fingerprint + OLED DIsplay |  | 2023-12-03 | 2023-12-03 | None | Not start | 20%
ESP Module + Fingerprint |  | 2023-12-03 | 2023-12-03 | None | Not start | 20%
ESP Module + OLED Display |  | 2023-12-03 | 2023-12-03 | None | Not start | 20%
Dicussing | Group |  |  | None | Not start | 30%
week 8 Retesting | [6 empty] | we must make up
Fingerprint + OLED DIsplay |  | 19/03/2023 | 19/03/2023 | None | Not start | 20%
ESP Module + Fingerprint |  | 19/03/2023 | 19/03/2023 | None | Not start | 20%
ESP Module + OLED Display |  | 19/03/2023 | 19/03/2023 | None | Not start | 20%
Dicussing | Group |  |  | None | Not start | 30%
week 9 Build | [6 empty] | we must make up
Hard ware |  | 26/03/2023 | 26/03/2023 | None | Not start | 30%
Hard ware |  | 26/03/2023 | 26/03/2023 | None | Not start | 30%
Hard ware |  | 26/03/2023 | 26/03/2023 | None | Not start | 30%
Dicussing | Group | 26/03/2024 | 26/03/2024 | None | Not start | 30%
Royal University of Phnom Penh
Attandent System Fingerprint QR Scan and Online Database
Faculty of Engineering